## Gantt Dashboard
GANTT CHART ¦ FLAG CAPTURE AGENT
TASK LIST / AGILE ITERATIONS | [5 empty] | OCT 2026 |  | NOV 2026 |  |  |  |  | DEC 2026 |  |  |  | JAN 2027
Task | Iteration | Status | Start date | End date | Days | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
Literature Research & API Understanding | Iteration 1 | Done | 2026-10-19 | 2026-10-22 | 4 | ●
GitHub Setup & Dev Diary | Iteration 1 | Done | 2026-10-19 | 2026-10-23 | 5 | ●
Baseline Agent Testing | Iteration 1 | Done | 2026-10-21 | 2026-10-25 | 5 | ●
Project Planning & Software Structure | Iteration 1 | Done | 2026-10-19 | 2026-10-25 | 7 | ●
Map Storage Implementation | Iteration 2 | In Progress | 2026-10-26 | 2026-11-05 | 11 |  | ● | ●
Visited Cells & Map Update Logic | Iteration 2 | Planned | 2026-11-02 | 2026-11-08 | 7 |  |  | ●
Frontier Exploration Design | Iteration 3 | Planned | 2026-11-09 |  | #VALUE! |  |  |  | ● | ● | ● | ● | ● | ● | ● | ● | ●
Information Gain Integration | Iteration 3 | Planned | 2026-11-16 | 2026-11-22 | 7 |  |  |  |  | ●
A* Pathfinding | Iteration 4 | Planned | 2026-11-23 | 2026-11-30 | 8 | [5 empty] | ● | ●
Dynamic Replanning for Blocked Routes | Iteration 4 | Planned | 2026-12-01 | 2026-12-06 | 6 | [6 empty] | ●
Flag Detection & Pickup Logic | Iteration 5 | Planned | 2026-12-07 | 2026-12-13 | 7 | [7 empty] | ●
Return-to-Base Logic | Iteration 5 | Planned | 2026-12-14 | 2026-12-20 | 7 | [8 empty] | ●
Full Agent Integration | Iteration 6 | Planned | 2026-12-17 | 2026-12-27 | 11 | [8 empty] | ● | ●
Testing & Debugging | Iteration 6 | Planned | 2026-12-21 | 2027-01-03 | 14 | [9 empty] | ● | ●
Optimization & Final DLL | Iteration 6 | Planned | 2026-12-28 | 2027-01-03 | 7 | [10 empty] | ●
Documentation & Final Submission | Iteration 7 | Planned | 2027-01-04 | 2027-01-07 | 4 | [11 empty] | ●
Legend: Cyan = Done ¦ Light blue = In Progress ¦ Deep teal = Planned ¦ Red = Blocked • Change Start, End, or Status to adjust the timeline colors.